## RACI
# | Step | Type | Requester (Employee) | PMS (Salesforce) | Administration Department | Section Manager | Department Director | PM Office (Strategy Office) | Budget Section | DG Office
1 | Create program request (draft) | Task | R
2 | Answer screening questions | Task | R
3 | Classify as Project or Initiative and score priority | System step |  | R
4 | Upload cost estimation file | Task | R
5 | Upload project scope (template) | Task | R
6 | Complete budget details and submit for approval | Task | R
7 | Collect and upload supplier quotations | Task |  |  | R
8 | Review request (Section Manager) | Approval |  |  |  | A
9 | Review request (Department Director) | Approval |  |  |  |  | A
10 | Review request (PM Office) | Approval | [5 empty] | A
11 | Create Project / Initiative record | System step |  | R
12 | Confirm budget availability | Approval | [6 empty] | A
13 | Endorse program (DG Office) | Approval | [7 empty] | A
14 | Notify requester (bilingual email) | Notification |  | R

## IT systems
# | Step | IT system
1 | Create program request (draft) | CRM (Salesforce)
2 | Answer screening questions
3 | Classify as Project or Initiative and score priority
4 | Upload cost estimation file
5 | Upload project scope (template) | Document Management
6 | Complete budget details and submit for approval | CRM (Salesforce)
7 | Collect and upload supplier quotations | Document Management
8 | Review request (Section Manager)
9 | Review request (Department Director)
10 | Review request (PM Office)
11 | Create Project / Initiative record
12 | Confirm budget availability
13 | Endorse program (DG Office)
14 | Notify requester (bilingual email)

## Steps
# | Step | Type | Role | IT system | Description | Processing | Waiting | SLA | Frequency | Cost | Inputs | Outputs
1 | Create program request (draft) | Task | Requester (Employee) | CRM (Salesforce) | In Program Requests > New: program name, description, justifications, strategic objective, program type (digital / non-digital), source of suggestion, nature (new / continuation), delivery options with advantages and disadvantages, link to internal operations or services, and the four 1–5 priority criteria. | 30 min | 0 min | 1 h | 4 | 20
2 | Answer screening questions | Task | Requester (Employee) |  |  | 20 min | 0 min | 40 min | 4 | 15
3 | Classify as Project or Initiative and score priority | System step | PMS (Salesforce) |  | Project when all screening answers are Yes and the approximate budget is at least AED 50,000 (threshold maintained by PM Office); otherwise Initiative. Evaluation Score and priority band are calculated from the four criteria.
4 | Upload cost estimation file | Task | Requester (Employee) |  | Cost Estimation File action: upload the available quotation and enter the estimated budget with Year 1–4 costs (must equal the estimated budget) and expected start and end dates (within 3 years). | 1 h | 1 d | 2 d 2 h | 2 | 40
5 | Upload project scope (template) | Task | Requester (Employee) | Document Management | Download the Project Scope template, complete it and upload it. The Administration Department is notified by email to collect quotations. | 2 h | 1 d | 2 d 4 h | 2 | 60
6 | Complete budget details and submit for approval | Task | Requester (Employee) | CRM (Salesforce) | Fill the budget breakdown, cost sharing, operating costs and expected financial return, then Submit for Approval with a comment. Also used to resubmit after a return for correction. | 15 min | 0 min | 30 min | 4 | 10
7 | Collect and upload supplier quotations | Task | Administration Department | Document Management | Open the request from the email link, use Upload Quotations to attach all quotations with a comment. Status becomes Quotations Uploaded and the request returns to the requester. | 4 h | 2 d | 4 d 8 h | 2 | 90
8 | Review request (Section Manager) | Approval | Section Manager |  | Check section-level alignment and completeness. Approve, Reject or Return for Correction (comment required). | 1 h | 1 d | 2 d 2 h | 4 | 80
9 | Review request (Department Director) | Approval | Department Director |  | Validate departmental priority and resource alignment. Approve, Reject or Return for Correction. | 1 h | 2 d | 4 d 2 h | 4 | 100
10 | Review request (PM Office) | Approval | PM Office (Strategy Office) |  | Check methodology adherence, classification, evaluation score and strategic alignment. Approve, Reject or Return for Correction. | 2 h | 2 d | 4 d 4 h | 4 | 150
11 | Create Project / Initiative record | System step | PMS (Salesforce) |  | PMS Project created automatically (ID PROJ-SPMO-YYYY-NNN), stage Initiation, linked to the request.
12 | Confirm budget availability | Approval | Budget Section |  | Validate financial feasibility and record the Approved Budget. Approve or Reject. | 1 h 30 min | 2 d | 4 d 3 h | 2 | 120
13 | Endorse program (DG Office) | Approval | DG Office |  | Strategic endorsement of programs above AED 50,000. Approve, or return for correction. | 1 h | 3 d | 6 d 2 h | 1 | 250
14 | Notify requester (bilingual email) | Notification | PMS (Salesforce) |  | Approval outcome and link to the new project, in English and Arabic.

## Legend
Description
R | Responsible: performs the step (lane or “performs” link)
A | Accountable: approves (performer of an approval step)
C.09 | Program Request Approval — Draft